## Critical path
Planning schedule for Online Events (Template)
Name of event: xxxxxxx
Date of event: xx/xx/xx
ACTIONS / TASKS | RESPONSIBLE | DEADLINE | COMPLETED
Event basics
Confirm the basic event details - timescales / event title / date and time of the event
Be clear on the objective/s of the event - what are the success factors / desired outcomes / business objectives
Confirm your event production team (the behind-the-scenes team) - the event producer, IT support contact, event support contact
Confirm your event team - your speakers / academics / facilitators
Set up regular working group meetings to ensure the event planning stays on track - consider setting up a team chat on MS Teams to allow documents to be shared / meeting notes to be recorded / as a communication tool on the day of the event
Event content and design
Consider the format of your online event - number of speakers / interview style / moderated panel discussion / interactive for all participants Tip: The expected size of the audience will help determine the format, for example, a fully interactive session might not be appropriate for a large audience)
Consider the reach of the event - what is the anticipated audience size? 20 or 10,000 participants?
Consider which features you might need to use - live streaming / interactive chat / Q&A / recording capability
Once you have considered the format and expected audience size of the event, select which online platform best to use (e.g. Zoom or MS Teams)
Plan the visuals for your online event: - Ensure engaging and easy to digest content (encourage the presenters / speakers to make their presentations succinct and engaging) - It's a good idea to create a slide introducing each presenter, including job title and organisation - Include a slide that gives a quick overview of the agenda and the topics to be covered - Aim for consistent design style with all presentations - use the same PowerPoint template, colour scheme and font style - Select an easy-to-read font and don't include any font size smaller than 24pt
Create the agenda and if possible, circulate to participants ahead of the event in order to stimulate engagement prior to the event
Devise schedule for logistical 'back of house' changes such as moving participants from the main event into virtual breakout rooms, etc
Input attendees into breakout groups ahead of the event if required
Categorise attendees into presenters and participants categories to limit access/abilities as required (e.g. mute all, screen sharing etc)
Registration process and participant communications
Create your invitee list - and consider other stakeholders who might wish to contribute relevant contacts to the list before registration goes live
Create your registration site / page using Eventbrite or an MS form for a more simple event Tip: The Events Team can set this up for you
Circulate the draft registration page to all main stakeholders for approval
Make registration site / page live Tip: Usually, 3-6 weeks pre-event allows a sufficient registration period for an online event
Monitor registrations and circulate participant lists to the event leads on a regular basis Tip: The Events Team can generate registration reports and updates
Draft and circulate Joining Instructions to all those who have registered to attend - ensure to include instructions on the online platform and how to access the meeting (include password / link to join) Tip: Circulate Joining Instructions for an online event no later than 3 working days prior
Ensure you adhere to GDPR and the data protection in relation to sharing attendee contact details and consent to recording events
Circulate the final participant list to the event team (day prior)
Promotion of event
Prepare / source content (copy, logos and any relevant images) for use on the registration page (Eventbrite) and for use in promotional platforms (e.g. Weekly Bulletin, College Newsletter, website event listings, internal or external mailing lists, etc.)
Identify the most relevant social media promotion channels (LinkedIn, Facebook, Twitter) and brief in Social Media / Event team who will promote your event on the official University's social platforms
Brief in PR Team - let them know main details of event and discuss what types of PR would be relevant
Promote the event via all relevant sources - at least 2-3 weeks in advance of an online event
Technical Resources / Support required
Identify online platform for the event to be hosted upon (Zoom or Teams)
If using MS Teams Live - complete the Live Event Set Up Request Form in order to set up the event with the IT Team Tip: Click on link below for the request form: https://universityofexeteruk.sharepoint.com/sites/SharePoint/SitePages/Live-events.aspx
Book AV support (if required) Tip: The AV Team are on hand to provide technical support with the use of Zoom and Teams
Book Recap (if required)
Consider using a professional online event facilitator to ensure a slick event, especially if the event includes a panel discussion or interaction amongst a large number of participants
Communications - Speakers / Presenters
Confirm all speaker / facilitator requirements pre-event and gain written consent if they are happy to be recorded
Provide guidance to speakers recording their talks (length of time, slide limit, abilities of the online platform etc)
Draft joining instructions with specific detail pertaining to speakers and presenters (confirm what their capabilities will be - mute participants / share screen / use chat / respond to questions / queue up content, etc)
Send joining instructions out to speakers and presenters (no later than 3-5 working days prior)
Event documentation
Complete an online event risk assessment prior to the event in order to create a secure online event Tip: The Events Toolkit contains a Risk Assessment Template for Online Events
Rehearse, test and prepare
Check content and prepare your speakers / presenters: Ensure that the intended content matches the invitation Discuss structure, timing, and flow with all involved Create a production script if relevant (identify each segment - the duration of each segment, the speaker and the technology features required) Prepare PowerPoint slides and template (if you are overseeing the content) Make sure all speakers have appropriate audio devices and are familiar and confident with the online platform being used
Test the digital platform (i.e.: Zoom, MS Teams) and check the required features are working correctly (i.e.: check how to record, check how to manage Q&A)
Hold a test run for all presenters, introduce everyone, run through all presentations in order to confirm the flow of the event
On the day of event
Request to meet with your team one hour before the online event to check everyone is ready and no final changes to the agenda
Perform a final sound check
Review the slide deck
Make sure polls, and any 'starter' questions are loaded into the platform before going live
Set up a Plan B – back-up audio and network.
Record the webinar and assign two people to create a backup recording.
Launch a 'splash screen' 15 minutes before going live
Mute all non-speakers
Send a welcome message to audience one to two minutes before starting the broadcast
Start on time, welcome the audience and deliver housekeeping notes
End on time, and thank the speakers and the audience.
Post Event
Hold a debrief call with event team (to follow up on post event actions)
Send all participants a post event survey if feedback is requested
Send a thank you email to all participants with a link to the recording of the event (if relevant)